## Sheet1
# | Page Name | Events | Actions | Resource | Estimated hrs | UI | Service | Start Date | End Date | Status | Comments
1 | Fresh Landing screen | Choose your plan Btn | need to get plans from backend and should goto choose your plan page | RK | 6 | design with static content | Not started | 2019-02-28 | 2019-02-28 | inprogress
2 | choose your plan | plans | need to display plans | Prashanna | 1 | design with static content | Not started | 2019-02-28 | 2019-02-28 | inprogress
3 | choose your plan | meal price per plan details | need to display plan price | Prashanna | 1 | design with static content | Not started | 2019-02-28 | 2019-02-28 | inprogress
4 | choose your plan | meal price per meal per plan details | need to display meal price per meal per plan price | Prashanna |  |  | Not started | 2019-02-28 | 2019-02-28 | inprogress
5 | choose your plan | shipping charges per trip per plan | need to display shipping charges per trip per plan | Prashanna |  |  | Not started | 2019-02-28 | 2019-02-28 | inprogress
6 | choose your plan | Select Btn | need to goto the customize your meal page | Prashanna | 2 | design with static content | Not started | 2019-02-28 | 2019-02-28 | inprogress
7 | customize your meal | # of meals per plan | need to get the # of plans as per plan | Prashanna | 3
8 | customize your meal | meal selection dropdown | need to display meal number. If already saved meal number option selected then it should display selected ingrediants for that perticular meal |  | 2
9 | customize your meal | Base slick-track | 1. need get from backend with price in 2nd line and name in 1st line 2. only one should select |  | 2
10 | customize your meal | Green slick-track | 1. need get from backend with price in 2nd line and name in 1st line 2. only one should select |  | 2
11 | customize your meal | Protein slick-track | 1. need get from backend with price in 2nd line and name in 1st line 2. only one should select |  | 2
12 | customize your meal | save btn | after select ingrediants from base, protein, and green slick-tracks should able to save the selected options per meal |  | 8
13 | customize your meal | Continue btn | after saving ingrediants for all meals then it should enable. When we click on continue btn it should goto the Logistics page. |  | 4
14 | Logistics page | delivery Address | need to fill the below check text boxes Streat name block name postal code , countey by default SG |  | 1
15 | Logistics page | Delivery Time | need to get time slots from backend and only one should select (radio btn) , this time slot is for all meals delivery. Need to display 24hrs format. |  | 2
16 | Logistics page | Meal Delivery dates | per meal customer can select delivery date. Better use calender to select date. |  | 1
17 | Logistics page | Continue btn | it should enable after selecting all address fields, delivery time slot, and delivey dates per meal. Change continue btn to check out and in btn it should display amount Ex: Check out (SG$ 75.00) |  | 4
18 | shipping / delivery | Fresh Accordian | need to display summary like below 1. delivery time slot for all meals 2. need to display meal # and delivery dates
19 | shipping / delivery | continue | after reviewing plz click continue btn, then it will open place your order accordian.
20 | place your order accordian. | orders summary | need to display meal plan and price need to display ingrdiants and additional amount remaining is same as grocery/ gourmet.